Frederick County Main Streets Public Art Project

Project Process

April 2019

Project Participants

- Brunswick Main Street

- Downtown Frederick Partnership

- Main Street Middletown

- Town of New Market

- Town of Thurmont

Project Timeline

May-June 2019			Artist Selection

Summer 2019 to Spring 2020		Artist/Team works with Partners/Fabrication begins

Spring/Summer 2020			Artworks installed at 5 sites

Summer 2021				Project Completion (one year installation)

Budget

$40,000 (?) (inclusive of administration, design fees and fabrication

Selection Panel

The Artist Selection Committee will be made up of representatives from each of the Main Streets in Frederick:

- Sophie Smith, Brunswick Main Street

- Kara Norman, Downtown Frederick Partnership

- Becky Axilbund, Main Street Middletown

- Maria Dalton, Town of New Market

- Vicki Grinder,  Town of Thurmont

Additional members to be invited to participate:

- Louise Kennelly, Frederick Arts Council

### John Fieseler, Tourism Council of Frederick County

Selection Process

Based on discussions with each Main Street representative, the Artist/Team Selection Process will be a two part process. The Selection Committee will meet twice during the Selection Process. A Request for Qualifications (RFQ) will be drafted to solicit regional artists (no travel compensation is available, but artists outside of Frederick County and Maryland are eligible to apply). Special consideration may be given to local/Maryland artists during the the selection process.

Based on these applications, up to five (5) artist/teams will be chosen by the Selection Committee to develop concepts/design proposals for the Art on Main Street Project. Each finalist team will be given a modest honorarium to develop concepts/designs (to be determined; $150-250 each?) to present at an in person interview with the Selection Panel. The Selection Panel will meet and interview each of the finalists and select one Artist/Team. This Artist/Team will provide artwork for each of the five (5) Main Street locations.

The Contract for the Artist/Team will be held by the Brunswick Main Street.

Two types of Project Proposals will be considered:

- Artworks owned by the Artist/Team that will be on temporary loan to each Main Street participant for the duration of the project installation period (one year). This would be similar to the ARTSites Program in Howard County.

These artworks would have a cohesive theme linking all of the Main Street sites and be easily identifiable as part of a County-wide project. Because this type of project may not require a lot of site specific design work and the Artist/Team could re-loan or sell the artwork after the loan period, this may be a cost effective way to borrow large scale pieces or pieces made of permanent materials (cast metal, stone, etc.) for each site. Once the year has been completed, the artwork would revert back to the ownership of the Artist.

- Site-specific artworks that would be created for each individual site by the Artist/Team. The artwork created, rather than a temporary loan, could be considered temporary because of the ephemeral nature of the materials used in addition to the one year commitment at each site. This type of artwork would still have a theme to guide the design process and could also be identifiable as part of a County-wide project.  However, each artwork could be created to connect specifically with each Main Street— its history and character.

Design Process

Once the Artist/Team is selected; they will meet with each Main Street program individually to determine the location and specifics of the Artwork.

Each Main Street participant shall have a Design Committee comprised of the Main Street coordinator and other community members that will work with the Artist/Team and Project Consultant to provide information, feedback and coordinate each site installation.

The Design Committee will work with the Artist/Team to determine the best site for the artwork and to obtain design approvals and permits for the artwork and artwork installation.

Fabrication/Installation

Installation of each artwork will be coordinated with the Project Consultant, the Artist/Team and the Main Street representative for each site based on constraints/other construction and opportunities to promote the project or other Main Street activities.

Project Completion

After the artwork has been installed for one year, the Artist will return to take down/remove the Artwork (unless plans have been made to extend the installation). The Contract with the Artist/Team will outline whether the artwork returns to the Artist/Team or remains the property of the Main Street.

Request for Qualifications

Frederick County Main Streets Public Art Project

April 2019

DRAFT

Opportunity

With support from the Tourism Council, Frederick County’s five Main Street Programs are collaborating on a project to bring temporary public art to each of its five Main Streets.  The Frederick Main Street partners are seeking an Artist/Team to design, fabricate, and install five temporary public artworks at each of the Frederick Main Streets.

The Main Streets included in the project are located in the following municipalities: Frederick, Brunswick, Thurmont, Middletown, and New Market.  While the five Main Street areas have some common characteristics, they each have a unique character and each offers a different downtown experience for visitors.

One Artist/Team will be selected to provide five (5) temporary public art pieces, one for each of the Main Street sites.  These must be five (5) unique public art pieces.

Project Vision

The Vision of the Main Street Public Art Project (shall we name it? “Art on Main” or the “HeART of Frederick”?) is to celebrate Frederick County’s downtowns, to create linkages between the five communities and to highlight the connections between their agricultural communities and downtowns—both today and into the future.

Project Goals

The Goals of the Main Street Public Art Project are:

- To highlight both the common threads of the Main Streets (what makes them “Frederick County”) and what makes each Main Street special.

- To encourage locals and tourists to visit and appreciate the offerings in each of the Main Street sites.

- To engage dialogue with the community about art and how it can enhance public spaces.

Site Location and Requirements
The Selected Artist/Team will be contracted to provide a unique public art piece for each of the five Main Street areas in Frederick.

The Selection Committee is open to the following types of temporary public art installations.

Artist/Teams must select one of the two types. All five sites must have the same type of artwork (either on loan or site specific).

- Artworks created and owned by the Artist/Team that will be on temporary loan to each Main Street participant for the duration of the project installation period (one year). Once the year has been completed, the artwork would revert back to the ownership of the Artist.

- Site-specific temporary artworks that will be created for each individual site by the Artist/Team. These pieces should reflect the characteristics of each Main Street site. Upon the completion of the one year installation, the Artist/Team must remove the artwork. The Main Street has the right to retain ownership of artwork if desired.

Themes and Styles and Materials

The artworks for the five sites should be thematically linked in a way that is easily identifiable to visitors who may visit the various sites.  How the artworks are connected is up to the Artist/Team.

Any materials/mediums used must conform to local and state (if applicable) regulations specific to the Main Street area. Different mediums may be used at different sites if appropriate. Materials used should be able to withstand outdoor conditions for at least one year without deterioration/degradation.

All artworks must be of low or no maintenance (funds are not available for cleaning, electricity or lighting, etc.).

About the Frederick Main Street Programs

The Frederick Main Street programs are among the 30 designated areas of the Main Street Maryland program. The program is a comprehensive downtown revitalization program created in 1998 by the Maryland Department of Housing and Community Development. The program strives to strengthen the economic potential of Maryland’s traditional main streets and neighborhoods. Using a competitive process, Main Street Maryland selects communities who have made a commitment to succeed and helps them improve the economy, appearance and image of their traditional downtown business districts.

For more information on each of the individual Main Streets in Frederick, see Attachment A. (Attachment A to be created).

Project Eligibility
All professional Artists or Artist Teams living in the mid-Atlantic region are eligible to apply; however, no travel compensation is available.

If Artists are applying as a Team, the Team should be listed on the application form, specifying a Team leader to receive notifications.

Selection Process

Up to Five (5) Finalists will be chosen by the Selection Panel to develop proposals for the five sites. After the Artist/Team has been selected, the alternate Artists/Teams will be awarded $xxx each.

Budget Details
The total Project Budget is $35,000. The Project Budget is inclusive of all costs associated with the Project, including but not limited to: artist fee and expenses (travel/lodging, printing, overhead, etc.), artwork fabrication (supplies, paint, scaffolding, etc.), storage/transportation (if applicable), installation, artwork removal, and insurance. Any expenses that exceed $35,000 will be the Artist’s responsibility.

Submission Procedures

1.  Application Process:

Applications must be submitted by date (May xx, 2019)

- Application Form (to be created)

- Estimated Project Budget. Estimated Budget should include all costs associated with the proposed Designs. (artist fees, supplies, fabrication, installation, etc.)

- Statement of Interest. Please state why you are interested in this project and how your experience and approach would benefit this Project.  If applying as a Team, please describe the collaborative experience and approach. (1,000 characters maximum)

- Resume or CV. 5,000 characters, including spaces, maximum. Teams must include resumes of all artists applying within 5,000 characters.

- References. Include at least three (3) art and/or design professionals who have detailed knowledge of the Artist’s work.  References must include contact name, organization/affiliation, address, telephone number, and e-mail for each reference.

- Examples of Previous Work.  Include a maximum eight (8) JPEG images, minimum five (5) JPEG submissions. Only ONE (1) image per JPEG, no composite images.

The applicant certifies that the information contained in the application, including all supporting documents and attachments, is true and correct to the best of his or her knowledge. Any fraudulent statement made in the application will be grounds for denying a commission. Frederick County Main Street partners reserves the right to reproduce images of Finalists’ proposal for its own print, digital, promotional and marketing needs.

​2. Finalists Selection and Process

The Selection Committee will review all applications and select as Finalists five (5) Artists or Artist Teams.

Finalists will be selected based on the following criteria:

- Aesthetic Excellence – The aesthetic quality of the artwork upholds the principles of art and design excellence, originality and innovation

- Artist Experience –  Experience in creating public art of similar scope and scale

- Understanding of the Project – Based upon the Statement of Interest

3. Final Design Selection

The five Finalists will be interviewed and will present their design proposals to the Selection Panel. Finalists will be evaluated during the interview based upon the above criteria as well as the following:

- Relevance/Theme  – The proposals must be appropriate to the sites, reflect the Main Streets  and Frederick County, thematically connected to each other

- Feasibility –The proposals must be able to be completed within the allotted Budget and within the time frame (all sites must be completed by June 2020).

Artist Award and Contract
The Selected Artist/Team will work closely with the:

The Selected Artist will be required to submit a detailed Budget of the Project for approval.

The Selected Artist will be required to carry liability insurance and name the Main Street partners as additional insured for the duration of the Project.

Artist shall retain intellectual property rights.

The Frederick Main Streets shall have the unconditional right to retain the proposal materials (drawings, illustrations) as part of the proposal commission, whether or not the artwork is selected for implementation. Full credit will be given to Artists or Artist teams if a proposal is disseminated by print or digital means

If utilizing the proposal for future public art applications, the Artist shall give credit to the Frederick County Main Street program.

Selection and Production Schedule: (tentative dates)

RFP Posted/Applications Accepted:  April 26, 2019

RFP Application Deadline:    May 17, 2019 (tentative)

Finalist Selection Process:   May-June 2019

Artist Award Notification:   June-July 2019

Artist Contracting Phase:    Summer 2019

Artwork Final Design Phase:    Winter/Spring 2020

Artwork Installation Period:     Spring/Summer 2020

Artwork Removal:       Spring/Summer 2021

Questions and Inquiries
All questions and inquiries must be in writing and directed to Susie Leong, Public Art Consultant, sleong@gmail.com

For site photos, visit: